# Draft Project Implementation Schedule

|  | Quarters, 20__ |  |  |  | Quarters, 20__ |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Tasks | First J F M | Second A M J | Third J A S | Fourth O N D | First J F M | Second A M J | Third J A S | Fourth O N D |
| Project design Commerce final design Complete project design Submit plans to DEQ Prepare bid documents Finalize acquisition |  |  |  |  |  |  |  |  |
| Advertisement for construction bid Review contract requirements Public bid advertisement Open bids and examine proposal Request construction debarment review Select contractor and award bid Conduct pre-construction conference Issue notice to proceed to contractor |  |  |  |  |  |  |  |  |
| Project construction Begin construction Monitor engineer and contractor Conduct labor compliance reviews Hold construction progress meetings Final inspection |  |  |  |  |  |  |  |  |
| Project close-out Submit final drawdown Project completion report/final certification Contract end date |  |  |  |  |  |  |  |  |